## Risk Register
Risk Identification |  |  | Qualitative Rating |  |  |  | Risk Response
Risk Title | Risk Description | Risk Category | Probability | Impact | Risk Score | Risk Ranking | Risk Response | Trigger | Risk Owner
API Unavailability | Due to LitPath AI's dependency on the Gemini AI API for semantic query processing and AI-generated overviews, an extended service outage, rate limiting, or API deprecation by Google could disable the system's core search functionality and prevent the project from meeting its primary acceptance criteria. | Technical / External | 4 | 5 | 20 | 1 | Implement response caching for high-frequency queries; establish a fallback degraded-mode search using ChromaDB vector similarity without Gemini AI; coordinate with DOST-STII to confirm API cost coverage before production deployment. | Gemini AI API returns persistent errors, exceeds rate limits, or announces deprecation during development or testing phases. | Charijoy Cempron
Search Relevance Failure | Due to the complexity of semantic search over specialized academic literature, the system's RAG pipeline requires continuous iterative refinement to produce results that consistently meet the team's internal relevance benchmarks. Failure to address low-relevance query patterns before formal usability testing could result in rework cycles that consume sprint capacity originally reserved for deployment activities. | Technical | 3.25 | 5 | 16.25 | 2 | Conduct iterative internal relevance evaluation throughout development using a defined test query set; refine LLM prompts continuously; perform pre-usability relevance testing at least two weeks before formal usability testing begins. | Internal relevance testing reveals consistent failures across the defined test query set, or early informal user feedback surfaces recurring irrelevant results. | Charijoy Cempron
LLM Hallucination | Due to the inherent probabilistic nature of large language models, the Gemini AI API may generate inaccurate, fabricated, or misleading summaries, citations, or search overviews that appear credible to users, undermining the system's reliability as an academic research tool and potentially causing DOST-STII to reject the deliverable during acceptance testing. | Technical / AI | 3 | 5 | 15 | 3 | Implement source-grounded prompting that constrains Gemini AI responses strictly to retrieved document content; display source citations alongside every AI-generated output; conduct targeted hallucination testing as part of the QA cycle using known dataset entries to verify output accuracy. | QA testing identifies AI-generated summaries or citations that do not correspond to actual content in the indexed dataset, or usability testing participants report misleading or fabricated search results. | Joshua Sta Ana
API Latency / Slow Response | Due to LitPath AI's reliance on external API calls to Gemini AI for query processing and result generation, slow API response times under load or degraded network conditions could cause search query response times to exceed the ten seconds threshold, failing the system's performance acceptance criterion even when the API is technically available. | Technical / External | 3.5 | 4 | 14 | 4 | Implement timeout handling with defined maximum wait thresholds; use asynchronous API calls to prevent blocking; cache responses for frequent or repeated queries; display partial results while full AI overview loads to maintain perceived performance. | API response times consistently exceed 10 seconds during internal load testing, or usability testing participants report noticeable delays between query submission and results display. | Charijoy Cempron
Dataset Provision Delay | Due to the project's reliance on DOST-STII to provide a representative sample dataset of theses and dissertations, any delay or inadequacy in the dataset handover could prevent the team from completing RAG pipeline validation, relevance testing, and system acceptance within the project timeline. | External | 3.25 | 4 | 13 | 5 | Confirm dataset delivery schedule with DOST-STII at the start of each major testing phase; request a preliminary sample early to identify format or volume issues; define minimum dataset requirements in writing with the Project Sponsor. | DOST-STII has not provided the required dataset within two weeks of the agreed handover date, or the dataset is insufficient in volume or metadata quality for testing. | Tracie Tomon
Cloud Hosting Delay | Due to the planned transition from the local Proxmox development environment to a cloud hosting environment managed by DOST-STII for final production deployment, delays in confirming the hosting setup or cost approvals could prevent the system from going live by the June-July 2026 deadline. | External / Schedule | 3 | 4 | 12 | 6 | Initiate cloud hosting discussions with DOST-STII no later than May 2026; document hosting requirements in the Statement of Work; maintain the Proxmox server as a fallback demo environment; escalate any delays immediately to the Project Sponsor. | DOST-STII has not confirmed the production hosting environment or cost coverage by May 15, 2026, or the cloud environment setup encounters technical blockers during pre-deployment testing. | Tracie Tomon
Database Inconsistency | Due to the system's use of Supabase (PostgreSQL) for relational data and ChromaDB for vector embeddings, a failure in data consistency between the two systems could corrupt search results, break the bookmarking feature, or prevent accurate citation generation. | Technical | 2.75 | 4 | 11 | 7 | Implement automated consistency checks between Supabase and ChromaDB after each data ingestion cycle; maintain backup storage on the HDD per the system design; establish a documented data recovery procedure; test database integrity in every sprint QA cycle. | Search results return mismatched or duplicate records; bookmarked items fail to load; ChromaDB embeddings become out of sync with Supabase document records. | Joshua Sta Ana
Data Loss in Ingestion | Due to the complexity of the data ingestion and embedding generation pipeline, failures during batch processing — such as interrupted ingestion jobs, malformed document records, or embedding errors — may result in theses or dissertations being silently omitted from the indexed dataset, causing incomplete search results without any visible system error. | Technical | 3 | 3.25 | 9.75 | 8 | Implement comprehensive ingestion logging with record-level success and failure tracking; add post-ingestion validation that compares source document count against indexed record count; implement retry mechanisms for failed embedding generations; alert the team if record count discrepancies exceed a defined threshold. | Post-ingestion validation reveals a mismatch between the number of source documents provided and the number of records successfully indexed in ChromaDB or Supabase. | Charijoy Cempron
Scope Creep | Due to DOST-STII's ability to submit feedback and change requests during the Feature Refinement and usability testing phases, uncontrolled additions beyond the agreed Statement of Work could consume the team's limited sprint capacity and jeopardize the June-July 2026 deadline. | Scope | 3 | 3 | 9 | 9 | Enforce the formal scope change control process for all client-initiated change requests; document and confirm all feature clarifications in writing before development; require Project Sponsor approval for any changes affecting schedule or budget. | DOST-STII requests a new feature or significant modification outside the defined scope in the Statement of Work during the testing or deployment phase. | Tracie Tomon
Data Privacy Non-Compliance | Due to the Data Privacy Act of 2012 (RA 10173) requirements applicable to LitPath AI, any failure to implement proper data handling for user accounts, search history, and admin access could result in a compliance violation that blocks formal project acceptance or requires significant post-deployment rework. | Compliance | 2 | 4.25 | 8.5 | 10 | Ensure all user authentication uses secure login with role-based access control and session management with secure tokens; keep public search anonymous; enforce HTTPS/SSL on all connections; conduct a compliance review led by the Security Lead before usability testing. | Security audit identifies unprotected user data, unsecured API endpoints, or missing authentication controls during internal testing. | Joshua Sta Ana
Dependency / Library Compatibility | Due to the project's reliance on a Python-based AI stack including SentenceTransformers, ChromaDB, LangChain-type utilities, and Supabase client libraries, updates or breaking changes to any of these dependencies could introduce runtime errors, degrade system performance, or require unplanned refactoring that consumes sprint capacity. | Technical | 2.25 | 3.75 | 8.44 | 11 | Pin all dependency versions in the project's requirements file and lock file; test all updates in the staging environment before applying to the development or production environment; monitor dependency changelogs for breaking changes before each sprint. | System errors occur after a library update or environment change, or a dependency announces a breaking change in an upcoming release that affects a core system component. | Charijoy Cempron
Key Resource Unavailability | Due to the four-member HecTech team having no external outsourcing capacity, the unexpected unavailability of a key technical resource due to illness, personal emergency, or academic withdrawal could significantly disrupt sprint delivery and system integration milestones. | Resource | 2 | 4 | 8 | 12 | Maintain up-to-date technical documentation for all system components; cross-train team members on critical modules within sprint capacity; redistribute tasks among remaining members in the event of a temporary absence; escalate to Project Sponsor if absence exceeds one sprint. | A team member is unable to perform assigned sprint tasks for more than three consecutive working days due to illness, personal emergency, or academic withdrawal. | Tracie Tomon
Search Performance Degradation | Due to the system's use of SentenceTransformers for embedding generation and ChromaDB for vector search, performance degradation under concurrent user load or large dataset volume could cause search query response times to exceed the required ten seconds threshold, failing the system performance acceptance criterion. | Technical | 2.25 | 3 | 6.75 | 13 | Conduct load and performance testing during the Usability Testing phase; optimize ChromaDB indexing and embedding retrieval pipelines; implement query result caching for high-frequency searches; address all performance bottlenecks before final deployment. | Internal load testing reveals average search response times exceeding ten seconds under simulated concurrent user conditions, or usability testing participants report noticeable delays. | Charijoy Cempron
Local Server Hardware Failure | Due to the project's use of a locally hosted Proxmox server for development and internal testing, hardware failure such as SSD failure or power interruption could result in loss of code, database records, or configuration that delays sprint delivery. | Technical | 2 | 3.25 | 6.5 | 14 | Maintain all source code in a remote Git repository with regular commits after every work session; back up the Supabase database and ChromaDB embeddings to the 500 GB HDD; document all server configuration settings to enable rapid environment recovery. | The Proxmox server becomes inaccessible for more than 24 hours, or a team member reports data loss or file corruption on the local development environment. | Joshua Sta Ana
API Cost Overrun | Due to the project's use of the Gemini AI API without a formal written cost commitment from DOST-STII, any unexpected spike in API usage during testing or deployment could result in costs that exceed the project's contingency reserve and interrupt system functionality. | Cost / External | 2 | 3 | 6 | 15 | Confirm DOST-STII's formal commitment to cover all cloud hosting and AI/LLM API costs in writing before transitioning to production; monitor API usage costs throughout testing; report any projected overruns to the Project Sponsor immediately. | DOST-STII requests a delay in API budget commitment, or Gemini AI API usage costs during testing exceed the informally estimated monthly threshold. | Tracie Tomon

## Risk Matrix
Risk Matrix
|  | IMPACT |  |  |  |  | RISK SUMMARY
|  | Very Low (1) | Low (2) | Moderate (3) | High (4) | Very High (5) | Rank | Risk Title | P avg | I avg | Score | Level
PROBABILITY | Very High (5) | Medium | High | High | Critical | Critical | 1 | API Unavailability | 4 | 5 | 20 | Critical
| High (4) | Low | Medium | High | #4 API Latency / Slow Response | #1 API Unavailability | 2 | Search Relevance Failure | 3.25 | 5 | 16.25 | High
| Moderate (3) | Low | Medium | #8 Data Loss in Ingestion #9 Scope Creep | #5 Dataset Provision Delay #6 Cloud Hosting Delay #7 Database Inconsistency | #2 Search Relevance Failure #3 LLM Hallucination | 3 | LLM Hallucination | 3 | 5 | 15 | High
| Low (2) | Low | Low | #13 Search Performance Degrad. #14 Local Server Hardware Failure #15 API Cost Overrun | #10 Data Privacy Non-Compliance #11 Dependency / Library Compat. #12 Key Resource Unavailability | High | 4 | API Latency / Slow Response | 3.5 | 4 | 14 | High
| Very Low (1) | Low | Low | Low | Low | Medium | 5 | Dataset Provision Delay | 3.25 | 4 | 13 | High
[7 empty] | 6 | Cloud Hosting Delay | 3 | 4 | 12 | High
| LEGEND | [5 empty] | 7 | Database Inconsistency | 2.75 | 4 | 11 | High
| Critical | Score 20–25 |  |  |  |  | 8 | Data Loss in Ingestion | 3 | 3.25 | 9.75 | Medium
| High | Score 10–19 |  |  |  |  | 9 | Scope Creep | 3 | 3 | 9 | Medium
| Medium | Score 5–9 |  |  |  |  | 10 | Data Privacy Non-Compliance | 2 | 4.25 | 8.5 | Medium
| Low | Score 1–4 |  |  |  |  | 11 | Dependency / Library Compat. | 2.25 | 3.75 | 8.44 | Medium
[7 empty] | 12 | Key Resource Unavailability | 2 | 4 | 8 | Medium
[7 empty] | 13 | Search Performance Degrad. | 2.25 | 3 | 6.75 | Medium
[7 empty] | 14 | Local Server Hardware Failure | 2 | 3.25 | 6.5 | Medium
[7 empty] | 15 | API Cost Overrun | 2 | 3 | 6 | Medium

## Voting Table
Risk Assessment Voting Table
Each team member independently assigned Probability (P) and Impact (I) ratings (scale 1–5) during the risk assessment meeting. Final scores are averaged.
Risk Identification |  |  | Probability Votes (1–5) |  |  |  |  | Impact Votes (1–5) |  |  |  |  | Final Score
Rank | Risk Title | Category | P - Tracie | P - Jenine | P - Charijoy | P - Joshua | P Average | I - Tracie | I - Jenine | I - Charijoy | I - Joshua | I Average | Final Score | Risk Level
1 | API Unavailability | Technical / External | 4 | 4 | 5 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 20 | Critical
2 | Search Relevance Failure | Technical | 3 | 3 | 4 | 3 | 3.25 | 5 | 5 | 5 | 5 | 5 | 16.25 | High
3 | LLM Hallucination | Technical / AI | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 15 | High
4 | API Latency / Slow Response | Technical / External | 3 | 4 | 4 | 3 | 3.5 | 4 | 4 | 4 | 4 | 4 | 14 | High
5 | Dataset Provision Delay | External | 3 | 3 | 3 | 4 | 3.25 | 4 | 4 | 4 | 4 | 4 | 13 | High
6 | Cloud Hosting Delay | External / Schedule | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 12 | High
7 | Database Inconsistency | Technical | 3 | 3 | 2 | 3 | 2.75 | 4 | 4 | 4 | 4 | 4 | 11 | High
8 | Data Loss in Ingestion | Technical | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3.25 | 9.75 | Medium
9 | Scope Creep | Scope | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | Medium
10 | Data Privacy Non-Compliance | Compliance | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 5 | 4.25 | 8.5 | Medium
11 | Dependency / Library Compatibility | Technical | 2 | 2 | 3 | 2 | 2.25 | 4 | 4 | 3 | 4 | 3.75 | 8.44 | Medium
12 | Key Resource Unavailability | Resource | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 8 | Medium
13 | Search Performance Degradation | Technical | 2 | 2 | 3 | 2 | 2.25 | 3 | 3 | 3 | 3 | 3 | 6.75 | Medium
14 | Local Server Hardware Failure | Technical | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 3.25 | 6.5 | Medium
15 | API Cost Overrun | Cost / External | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 6 | Medium

## Rating Scale
Probability & Impact Rating Scale
Rating | Probability Descriptor | Probability Criteria | Impact Descriptor | Impact Criteria
1 | Very Low | Risk event is highly unlikely; no historical precedent within the project context and existing controls make occurrence improbable. | Very Low | Negligible effect on project objectives; easily absorbed within existing sprint capacity with no schedule or cost impact.
2 | Low | Risk event is unlikely but possible; limited exposure or conditions are largely within the team's control. | Low | Minor effect; resolvable within sprint capacity with minimal schedule adjustment.
3 | Moderate | Risk event is possible; some exposure exists due to external dependencies or known project constraints outside the team's direct control. | Moderate | Noticeable effect on schedule, cost, or quality; requires corrective action within the sprint cycle.
4 | High | Risk event is likely; strong dependency on uncontrolled external factors or recurring conditions increase probability. | High | Significant effect; threatens a project milestone or acceptance criterion and requires escalation to the Project Sponsor.
5 | Very High | Risk event is very likely or near-certain; critical dependency exists with no current mitigation in place. | Critical | Severe effect; directly blocks project delivery, formal acceptance, or deployment.
Risk Score Color Legend (Score = P avg × I avg, scale 1–25)
Low | Score 1.00 – 4.99
Medium | Score 5.00 – 9.99
High | Score 10.00 – 19.99
Critical | Score 20.00 – 25.00